## Sheet1
Online Exam Development
Task | Task Priority | ~#of Days to Comp | Actual #of Days Completed | Start Date | End Date | Actual Start Date | Actual End Date
Create database and Tables | High | 1 |  | 2022-06-14 | 2022-06-15
Exam Creator and Examinee Sign-Up Validations | High | 1 |  | 2022-06-15 | 2022-06-16
Login validations | High | 1 |  | 2022-06-16 | 2022-06-17
View Exam Creator Dashboard | High | 1 |  | 2022-06-17 | 2022-06-18
View Examinee Dashboard | High | 1 |  | 2022-06-20 | 2022-06-21
Create Exam | High | 5 |  | 2022-06-21 | 2022-06-27
View Created Exam | High | 1 |  | 2022-06-28 | 2022-06-29
View Exams to Take | High | 1 |  | 2022-06-29 | 2022-06-30
Take Exam | High | 5 |  | 2022-06-30 | 2022-07-07
Compute and display score | High | 1 |  | 2022-07-07 | 2022-07-08
Set exam settings | Medium | 1 |  | 2022-07-08 | 2022-07-11
Exam Creator summary of scores | Medium | 1 |  | 2022-07-11 | 2022-07-12
Examinee view exam scores | Medium | 1 |  | 2022-07-12 | 2022-07-13
Add Category | Medium | 1 |  | 2022-07-13 | 2022-07-14
Add Subject | Medium | 1 |  | 2022-07-14 | 2022-07-15
Edit Category | Medium | 1 |  | 2022-07-15 | 2022-07-18
Edit Subject | Medium | 1 |  | 2022-07-18 | 2022-07-19
Exam Creator Update Profile | Medium | 1 |  | 2022-07-19 | 2022-07-20
Examinee Update Profile | Medium | 1 |  | 2022-07-20 | 2022-07-21
Delete Created Exam | Low | 1 |  | 2022-07-21 | 2022-07-22
Delete Category | Low | 1 |  | 2022-07-22 | 2022-07-25
Delete Subject | Low | 1 |  | 2022-07-25 | 2022-07-26